# Active Home — Enterprise Technical Task (TT)

## Housing & Construction Advertising Marketplace — Uzbekistan (Version 1)

Document type: Enterprise Technical Task — the primary execution and acceptance document translating the approved architecture into an implementation plan. Version: v1.0 Status: Draft for client/architecture review — execution-ready Authoritative upstream sources (immutable): the full approved suite — Baseline v1.1 (ADR-001), BRD, Vision & Scope, SRS, DDD Domain Model, Configuration & Metadata Framework, SAD, Database Architecture & Logical Data Model, Physical Database Design & ERD, API Architecture & Integration Specification, OpenAPI 3.1 Specification, Security Architecture & Threat Model, Infrastructure & Deployment Architecture, DevSecOps Architecture & Delivery Strategy, AI-Assisted Development & Engineering Playbook, Frontend Architecture & Engineering Handbook, Frontend UI/UX Functional Specification, Frontend Component Library & Design System, Backend Architecture & Engineering Handbook.

Change-control statement. This Technical Task introduces no new requirement, redesigns no architecture, and modifies no API, schema, or security control. It consolidates the approved documents into one execution contract: what will be built, how it is organised, how it is accepted, and what "done" means. Every deliverable, module, and acceptance criterion traces to an approved source and is cited. Where the source documents already decide a matter, this TT restates and references it; it decides only execution structure (module packaging, milestones, acceptance gates). It uses RFC-2119 language; module/deliverable ids (M-nn, DLV-nn) and acceptance-criteria ids (AC-*) are stable references for planning and tracking.

Primary audience & use. Client, Product Owner, Business Analyst, Project Manager, backend/frontend/QA/DevOps engineers, and AI coding agents. Used for development planning, client acceptance, progress tracking, AI-assisted implementation, QA, and final delivery. It is the single index into the approved suite: each section points to the authoritative document for detail rather than restating it.

# 1. Project Overview

1.1 Purpose. Build Active Home, a configuration-driven classified-advertisements marketplace for Uzbekistan focused on construction, housing, renovation, building materials, manufacturers, and service providers — a web platform (SSR, mobile-first, uz/ru/en with dual-script Uzbek) where individuals and businesses publish, discover, and transact around listings (BRD, Vision & Scope).

1.2 Business objectives. Establish a trusted, searchable marketplace with verified business presence; enable Product Owners to evolve the catalogue, forms, plans, and rules without redeployment (the configuration-driven core, DEC-21); generate revenue via offline-billed subscriptions and listing promotions; reach Phase-1 scale reliably on a modest budget with a clear growth path (Baseline drivers).

1.3 Scope. Delivery of the complete approved system: web frontend, backend modular monolith (13 bounded contexts), PostgreSQL data layer, OpenSearch discovery, Redis, MinIO media, provider integrations (Google/Eskiz/Yandex/email/web-push), the Product-Owner configuration portal, the administration/moderation portal, deployment, and documentation.

1.4 Expected outcomes. A production-deployed platform meeting the SRS functional set and the NFR targets (search < 500 ms p95, interactive API < 300 ms p95, 99.9% availability, WCAG 2.2 AA, uz/ru/en), operable by non-technical Product Owners for business change, and maintainable/extensible by human and AI contributors under the Engineering Playbooks.

1.5 Phase 1 scope (in). Identity & auth (phone-OTP/email/Google); business profiles & paid verification; listings (advertisement/product/service) with the seven-state lifecycle; configurable categories & dynamic forms; media (images only); search (full-text, faceted, geo/radius, cross-script, suggestions); two-party listing-scoped messaging with phone-reveal/block/report; notifications (email/web-push/SMS); offline-billed subscriptions & promotions & banner placements; moderation & trust-safety; analytics/audit; the configuration portal (eight entities, Head+Version lifecycle); the administration portal.

1.6 Out of scope (Phase 1). Native mobile apps; online payment gateway (billing is offline); AI-powered recommendations; Reviews & reputation (Phase 2, DEC-03); Kubernetes deployment (Phase 2); multi-country/multi-currency; video/PDF media (images only, DEC-10). Full list in §20.

# 2. Deliverables

Top-level deliverables (DLV-nn); detail in the referenced sections.

| ID | Deliverable | Description | Reference |
| --- | --- | --- | --- |
| DLV-01 | Web Application | Next.js SSR/CSR app (uz/ru/en, mobile-first, WCAG AA) | §8; Frontend Handbook/UI-UX/Design-System |
| DLV-02 | Backend API | FastAPI modular monolith, 13 modules, REST per OpenAPI | §9, §11; Backend Handbook, API Arch |
| DLV-03 | Frontend | Component library + screens + dynamic form engine | §8; Design System, UI/UX Spec |
| DLV-04 | Database | PostgreSQL 17, 13 schemas, migrations, seed/config data | §10; Physical DB Design |
| DLV-05 | Search | OpenSearch read model + indexing pipeline + DB fallback | §9, §12 |
| DLV-06 | Internal Messaging | Realtime WSS chat + REST history, block/report/phone-reveal | §3 (M-09), §9 |
| DLV-07 | Administration Portal | Moderation, verification, users, audit, reports, dashboard | §3 (M-10), §8 |
| DLV-08 | Product Owner Configuration Portal | Head+Version authoring for 8 config entities | §3 (M-11), §7 |
| DLV-09 | Documentation | API, deployment, admin, product-owner, developer guides | §15 |
| DLV-10 | Deployment | Docker/Compose, Nginx, TLS, backups, production launch | §13; Infrastructure, DevSecOps |
| DLV-11 | Source Code | Full repository (backend+frontend+IaC+tests) under the Playbooks | §9, §14; Playbook |
| DLV-12 | Test Suites | Unit/integration/API/frontend/E2E + acceptance packs | §14; DevSecOps |
| DLV-13 | Integrations | Google, Eskiz, Yandex, email, web-push, MinIO adapters | §12 |
| DLV-14 | CI/CD Pipeline | GitHub Actions gates + CD to staging/prod | §13; DevSecOps |

# 3. Functional Modules

The platform is implemented as thirteen modules mapped 1:1 to the bounded contexts (SAD §7, Backend Handbook). Each M-nn below specifies purpose, functional scope, inputs, outputs, dependencies, APIs (OpenAPI tags), database entities (schema), configuration dependencies, and acceptance criteria (AC). Detail lives in the cited documents; this is the execution index.

### M-01 Identity & Access (BC-01)

- Purpose: Accounts, authentication, sessions, acting-context, role assignment. Scope: phone-OTP/email/Google auth, session lifecycle, multi-profile acting-context, permission reflection (FR-AUTH-001…006, FR-USER-001…005).

- Inputs: registration/login credentials, OTP, Google code. Outputs: session, account, reflected permissions, domain events (UserRegistered, AccountSuspended).

- Dependencies: configuration (roles), Eskiz (OTP), Google. APIs: Authentication, Users. DB: identity schema. Config deps: role definitions, permission catalogue.

- AC: all three auth methods issue a server-side session; OTP throttled; Google links by verified email (no duplicate); acting-context switch scopes writes; account closure anonymises (not deletes); invariants I-09/I-10 tested.

### M-02 Business Profiles & Verification (BC-02)

- Purpose: Company profiles (8 types), portfolios, team, paid verification. Scope: FR-PROF-001…007.

- Inputs: profile data, portfolio images, verification docs + eligibility entitlement. Outputs: profiles, verification cases, BusinessVerified events.

- Dependencies: identity, media, billing (eligibility). APIs: Business Profiles. DB: profiles. Config deps: profile-type presentation, verification product.

- AC: one account owns many profiles; verification requires active eligibility (I-12); badge issued/expired per rules; documents images-only; SLA tracked.

### M-03 Catalog & Listings (BC-03)

- Purpose: Listings (advertisement/product/service), lifecycle, favorites. Scope: FR-ADV-001…010.

- Inputs: listing data + AttributeMap, images, category/form binding. Outputs: listings, transitions, ListingPublished/lifecycle events, promotion projection.

- Dependencies: configuration (category+form), media, identity, billing (promotion). APIs: Listings, Favorites. DB: catalog. Config deps: categories, form definitions.

- AC: seven-state lifecycle enforced (I-05); ≤10 images (I-04); attributes validated against bound form version (I-07); quota enforced (I-08); post-publication moderation (BRULE-17); ownership scoping.

### M-04 Configuration (BC-04)

- Purpose: The eight config entities, Head+Version lifecycle, snapshot distribution. Scope: Configuration Framework in full.

- Inputs: config definition documents. Outputs: published versions, snapshots, ConfigurationChanged events, audit entries.

- Dependencies: none inbound (leaf-free hub). APIs: Configuration (Admin). DB: configuration. Config deps: the whitelist registry [P] (code).

- AC: draft→validate→publish→rollback with maker–checker on controlled track; whitelist gate rejects non-catalogue entries (I-16); published versions immutable; every publish audited; snapshots distributed.

### M-05 Search & Discovery (BC-05)

- Purpose: Full-text, faceted, geo/radius, cross-script discovery. Scope: FR-SRCH-001…005.

- Inputs: catalog/profile events (indexing), query params. Outputs: ranked results, facets, suggestions.

- Dependencies: configuration (facets/sorts), OpenSearch, Yandex (geocode). APIs: Search. DB: search (checkpoint/ledger only). Config deps: search configuration snapshot.

- AC: cross-script match (DEC-19); facets from config; promoted labelled+capped (I-17); < 500 ms p95; DB fallback on index outage (QR-05).

### M-06 Media (BC-06)

- Purpose: Image upload/validation/processing/delivery. Scope: FR-MEDIA-001…004 (images only).

- Inputs: presigned uploads. Outputs: clean assets + variants, scan/processing status events.

- Dependencies: MinIO, malware scanner, CDN. APIs: Media. DB: media. Config deps: image whitelist.

- AC: images-only enforced (DEC-10); malware scan + EXIF strip before delivery (I-20); quarantined never served; non-blocking processing (QR-05); presigned direct upload.

### M-07 Messaging & Contact (BC-07)

- Purpose: Two-party listing chat, phone reveal, block, report. Scope: FR-MSG-001…004.

- Inputs: messages, block/report actions. Outputs: conversations/messages, ChatInitiated/PhoneRevealed events.

- Dependencies: identity, realtime tier, Redis pub/sub. APIs: Messaging. DB: messaging. Config deps: none (rate limits are policy).

- AC: exactly two participants (I-19); phone reveal privacy-gated (BRULE-13); blocks consulted on every send; rate-limited (BR-MSG-03); realtime with REST fallback.

### M-08 Billing & Entitlements (BC-08)

- Purpose: Products/plans, orders, invoices, entitlements — offline billing. Scope: FR-BILL-001…003, FR-SUBS-001…004.

- Inputs: orders, operator payment confirmation. Outputs: invoices, entitlements, EntitlementActivated events.

- Dependencies: configuration (products), identity/profiles. APIs: Billing. DB: billing. Config deps: product definitions (6 types).

- AC: order freezes ProductSnapshot (I-07); offline invoice + operator confirmation (DEC-02); entitlement activates on confirmed payment (I-14); no payment gateway; six product types.

### M-09 Notifications (BC-10)

- Purpose: Email/web-push/SMS delivery, preferences. Scope: FR-NOTIF-001…004.

- Inputs: domain events, templates. Outputs: rendered, dispatched notifications.

- Dependencies: configuration (templates), email/web-push/Eskiz. APIs: Notifications. DB: notifications. Config deps: notification templates.

- AC: template+preference resolution; OTP always SMS; content frozen at dispatch; preferences honored; per-recipient records.

### M-10 Administration & Moderation (BC-11 + BC-12)

- Purpose: Operator composition — moderation, verification queue, user mgmt, audit, reports, dashboard. Scope: FR-MOD-001…005, FR-ADMIN-*, FR-AUDIT-002.

- Inputs: operator actions. Outputs: moderation cases/actions, decisions, audit entries.

- Dependencies: all operator-facing modules' interfaces. APIs: Administration. DB: moderation, admin, analytics. Config deps: roles/permissions.

- AC: closed moderation verb set (BR-MOD-02); every action audited (I-22); verification decisions issue badges; user suspend/reactivate; audit read-only; dashboard KPIs.

### M-11 Product Owner Configuration Portal (frontend of BC-04)

- Purpose: UI for the eight config entities (Head+Version). Scope: Configuration Framework + UI/UX §5.

- AC: generic authoring UI over the config API; draft/validate/publish/rollback/compare/import-export; maker–checker states; no hardcoded entity editors.

### M-12 Analytics & Audit (BC-13)

- Purpose: Append-only audit + metric sinks, statistics, reports. Scope: DEC-06, I-22, FR-ANALYTICS-002.

- AC: closed metric vocabulary; audit immutable/partitioned; listing statistics projection; fixed report set.

### M-13 Ad-Serving / Banners (BC-09)

- Purpose: Banner campaigns/placement (DEC-23 descope candidate). Scope: FR-BANNER-001…003.

- AC: campaigns gated by booking entitlement (I-21); serving selection; deletable as a unit without breaking other modules (descope safety).

Cross-module acceptance: import boundaries enforced (no cross-module DB/internal access — DEC-22); one aggregate per transaction + outbox (no dual-write — DEC-09); all invariants I-01…I-24 have passing tests.

# 4. Functional Requirements Mapping

Every SRS functional requirement maps to Module / Backend / Frontend / DB / API / Acceptance. The table is grouped by FR family; nothing is unmapped (§23 verifies completeness). Detail per FR lives in the SRS; this is the execution cross-reference.

| FR family | Module | Backend (module layer) | Frontend (screens) | DB (schema) | API (tag) | Acceptance (summary) |
| --- | --- | --- | --- | --- | --- | --- |
| FR-AUTH-001…006 (auth/session/recovery) | M-01 | identity domain/app/infra | Login/Register/OTP/Recover | identity | Authentication | 3 methods issue session; OTP throttle; Google links; recovery |
| FR-USER-001…005 (profile/prefs/sessions/closure) | M-01 | identity | Profile/Settings/Sessions | identity | Users | edit profile; prefs; device list; anonymised closure |
| FR-PROF-001…007 (profiles/portfolio/verify/badge) | M-02 | profiles | Business profile/portfolio/verification | profiles | Business Profiles | multi-profile; verification w/ eligibility; badge lifecycle |
| FR-ADV-001…010 (listing CRUD/lifecycle/stats) | M-03 | catalog | Wizard/My Ads/Detail | catalog | Listings | 7-state lifecycle; ≤10 images; quota; attribute validation; stats |
| FR-CAT / FR-FORM (categories/forms) | M-04/M-03 | configuration/catalog | Category nav / dynamic form | configuration | Categories/Configuration | taxonomy + bound form; dynamic render |
| FR-SRCH-001…005 (search/facets/geo/cross-script) | M-05 | search | Search/Facets/Map | search+catalog | Search | facets from config; cross-script; geo; promoted cap; fallback |
| FR-MEDIA-001…004 (upload/validate/scan) | M-06 | media | Uploader/Gallery | media | Media | images-only; scan+EXIF; quarantine; non-blocking |
| FR-MSG-001…004 (chat/phone/block) | M-07 | messaging | Chat/Conversations | messaging | Messaging | 2-party; phone-reveal gate; block; rate limit |
| FR-BILL-001…003 / FR-SUBS-001…004 (orders/invoices/entitlements/plans) | M-08 | billing | Subscription/Plans/Invoices | billing | Billing | offline invoice; operator confirm; entitlement activation; quotas |
| FR-NOTIF-001…004 (notifications/prefs) | M-09 | notifications | Notification center/prefs | notifications | Notifications | multi-channel; template+prefs; OTP via SMS |
| FR-MOD-001…005 (report/flag/moderate) | M-10 | moderation | Moderation queue/case | moderation | Administration | report routing; closed verbs; audited actions |
| FR-ADMIN-* / FR-AUDIT-002 (admin/audit/reports) | M-10/M-12 | admin/analytics | Admin dashboard/users/audit/reports | admin/analytics | Administration | user mgmt; audit query; reports; dashboard |
| FR-ANALYTICS-002 (listing stats) | M-12 | analytics | Statistics | analytics | Listings/Administration | metric projection; owner stats |
| FR-BANNER-001…003 (banners) | M-13 | ads | (admin campaign UI) | ads | (Administration) | booking-gated; serving; descope-safe |
| FR-CFG-* (configuration lifecycle) | M-04/M-11 | configuration | Config portal | configuration | Configuration | Head+Version; validate/publish/rollback; whitelist gate |

Rule: each concrete SRS FR id is enumerated in the traceability matrix (§21) with its acceptance criterion; this grouped table is the module-level view. Any FR discovered unmapped during build is a defect resolved before the affected milestone closes (§17).

# 5. Non-Functional Requirements Mapping

Every NFR maps to concrete implementation tasks and a verification method.

| NFR family | Requirement (approved) | Implementation tasks | Verified by |
| --- | --- | --- | --- |
| Performance | search < 500 ms p95; interactive API < 300 ms p95 (NFR-PERF-001/002) | OpenSearch read model; Redis caching; designed indexes (PD §8); keyset pagination; RSC/streaming; virtualization | Load/perf tests; CD health SLO check; EXPLAIN in CI for hot queries |
| Security | default-deny authz; TLS; images-only; secrets; audit (NFR-SEC-001…005, NFR-LOG-001) | 4-gate authz; per-module DB roles (PD-06); scan+EXIF; secrets store; immutability triggers (PD-07); rate limits | Security gates QG-07/08; authz matrix (release gate); pen test |
| Availability | 99.9% monthly; RPO ≤ 15m / RTO ≤ 4h (NFR-AVAIL-001, NFR-REL-001) | health/readiness; restart policies; rolling deploy; PITR backups; graceful degradation (QR-05) | Uptime monitor; restore drills; degradation tests |
| Scalability | 10k→100k users, 100k→1M listings without redesign (NFR-SCALE-001/002) | stateless tiers; externalised state; partitioned sinks; read-replica-ready | Load tests; architecture review |
| Maintainability | config changes without deploy; modular isolation (NFR-MAINT-001) | configuration-driven rendering; import-linter boundaries; expand/contract migrations | Config-change tests; QG-05; migration gate QG-09 |
| Accessibility | WCAG 2.2 AA (NFR-ACC-001) | semantic components; keyboard/focus; contrast tokens; axe in CI | axe gate; manual SR/keyboard audits |
| Localization | uz-Latn/uz-Cyrl/ru/en; dual-script (NFR-LOC-001, DEC-19) | i18n catalogues; LocalizedText; cross-script search; glyph-complete fonts | i18n tests; locale E2E; cross-script search tests |
| Observability-ready | health/logs/metrics (DEC-15, QR-07) | health/readiness endpoints; structured JSON logs; metric hooks | Smoke tests; log review |

# 6. User Roles

Roles are configured compositions of a fixed permission catalogue (Configuration Framework §7); the platform ships permission meaning in code [P] and role composition in configuration [C]. Implementation reflects permission keys to shape UI; the backend enforces default-deny (Security §4).

| Role | Nature | Implementation requirement |
| --- | --- | --- |
| Guest | unauthenticated | Read-only public content (browse/search/detail/business pages/static); no session; SSR/SEO. |
| Registered User | base authenticated role | Own listings, favorites, messaging, notifications, profile/settings; personal acting-context. |
| Business Account | acting as a business profile | Business management, portfolio, team, subscription, verification, stats; scoped to the acting profile. |
| Manufacturer / Seller | profile types, not separate roles | Two of the eight closed profile types (M-02); rendered/labelled from config; same capabilities as a business account with type-specific presentation. Not hardcoded role logic. |
| Product Owner | operator (config-management + Super-Admin for roles/settings) | Configuration portal (M-11); maker–checker on controlled track. |
| Moderator | operator (moderation permission subset) | Moderation queue/actions (closed verbs); no billing/config keys. |
| Administrator | operator (broad permission set) | User mgmt, verification, moderation, billing confirmation, audit, reports. |

Configurable-roles impact (mandatory implementation note): no role→capability map is hardcoded anywhere (backend or frontend). New roles/permission compositions are created as configuration and take effect without deployment; adding a permission key is a code change requiring the whitelist + tests (I-16). "Manufacturer"/"Seller" are profile types (closed [P] set), and the UI must render them from configuration, never as bespoke pages (UI/UX §21 reconciliation).

# 7. Dynamic Configuration

Mandatory. The platform's defining property: business variability is data, not code (DEC-21, NFR-MAINT-001). This section fixes what is configurable [C] vs implemented [P].

| Entity | Configurable [C] (no deploy) | Implemented in code [P] (release + ADR) | Portal (M-11) |
| --- | --- | --- | --- |
| Categories | tree, names (localized), order, form binding, status | tree mechanics, path/slug rules | CRUD + version + publish/rollback |
| Dynamic Forms | sections, fields, order, labels, facet-eligibility | the form-render engine, layout mechanics | form builder + preview |
| Dynamic Fields | field instances per form | field types (whitelist) + their renderers | inside form editor |
| Validation Rules | validator bindings + params per field | validator types (whitelist), safe patterns | inside form editor |
| Roles | permission-key compositions | permission keys (catalogue) + evaluation | role editor (Super-Admin) |
| Permission Groups | author-time bundles | flattening-at-publish mechanism | group editor |
| Business Types | presentation/labels of the 8 types | the 8-type set (closed) | type presentation editor |
| Subscription Plans | plan instances, price, term, quotas, benefits | the 6 product types, entitlement mechanics | product editor |
| Feature Flags | typed on/off toggles (controlled track) | the code behind each flag (security-neutral) | settings editor |
| Notification Templates | subject/body per EventKey+channel+locale, tokens | EventKey set, rendering/dispatch | template editor + preview |
| SEO Templates | meta/title patterns, static pages | rendering pipeline | settings (keyed docs) |
| Platform Settings | typed key→value, nav, homepage layout, brand | settings schema, closed keys | settings editor |

Implementation rules: configuration is authored via M-04's Head+Version lifecycle; consumed as Redis-cached snapshots; the whitelist gate is a security boundary (I-16) — configuration can never add logic, permissions, or lifecycle states. Frontend renders every item above from snapshots (FAIR-01/08); a hardcoded category/plan/menu/role is a defect.

# 8. Frontend Deliverables

Work is broken into pages/features per the UI/UX Functional Specification (its §1–§21 is the authoritative screen spec) and built from the Design System components. Each page ships with all four state classes (loading/empty/error/success), responsive behaviour, and WCAG AA. Summary index (full spec in UI/UX doc):

| Page/feature group | Components | APIs (operationId) | Validation | States & responsive |
| --- | --- | --- | --- | --- |
| Public (home, search, category, listing detail, business profile, static, 404/500) | AdvertisementCard, SearchBar, FacetPanel, MediaGallery, Map | searchListingsGet, getListing, getCategoryForm, getBusinessProfile, suggest | query/param typing | SSR/SEO; skeletons; empty/degraded; mobile-first |
| Auth (login, register, OTP, recover, Google) | AuthLayout, FormField, Input, Button | requestOtp/verifyOtp, registerEmail, loginEmail, loginGoogle, startRecovery | phone/email/OTP patterns | throttle UX; generic errors |
| User dashboard (dashboard, my ads, favorites, messages, notifications, saved searches, profile, settings) | DataTable, Card, ChatWindow, NotificationPanel | listMyListings, changeListingStatus, listFavorites, listConversations, updateMe, updatePreferences | ownership/state | per-tab empty; optimistic; two-pane↔stacked |
| Business dashboard (profile, employees, ads, subscription, verification, statistics, messages, settings) | BusinessCard, PlanCard, StatisticsCard, MediaUploader | getBusinessProfile, listTeamMembers, listProducts, requestVerification, getListingStatistics | eligibility/quota | scoped to acting profile |
| Advertisement Creation Wizard | DynamicForm engine, MediaUploader, LocationPicker | getCategoryForm, initMediaUpload, createListing, changeListingStatus | dynamic-form (config) | multi-step; autosave draft; version-bound form |
| Product Owner portal (8 config entities) | ConfigVersionTimeline, ConfigDraftEditor | listConfigHeads, createConfigDraft, validateConfigVersion, publishConfigVersion, rollbackConfig | config gate (server) | generic editors; maker–checker; desktop-first |
| Admin/Moderator (dashboard, users, verification, moderation, ads mgmt, billing, audit, reports) | QueueList, ModerationCaseCard, AuditLogTable, DashboardWidget | queryAuditLog, listModerationQueue, applyModerationAction, decideVerification, confirmInvoicePayment | permission-gated | virtualized tables; audited actions |

Frontend acceptance: every screen matches the UI/UX spec; components are library components (no duplication); dynamic content rendered from config/OpenAPI types; axe-clean; the FAIR/DS-AI/UX-AI rules pass in CI.

# 9. Backend Deliverables

Per module (M-01…M-13), each layer delivered per the Backend Handbook & SAD:

- Domain: aggregates, value objects, domain events, policies, and the invariants I-01…I-24 as guarded behaviour + tests (pure, no I/O). Deliverable per module.

- Application: use cases (commands/queries) + ports (repository, provider); one aggregate per transaction + outbox. Deliverable per module.

- Infrastructure: SQLAlchemy 2.x repository adapters (per-module schema/role), provider adapters (behind ports), transactional outbox writer, ProcessedEvent ledgers. Deliverable per module.

- API: FastAPI routers at interfaces/ implementing the OpenAPI operations exactly; DTOs (not aggregates); the 4-gate authorization; the Problem error envelope. Deliverable per module.

- Background jobs (workers): outbox dispatch, search indexing, media processing, notification dispatch, scheduled sweeps (expiry/entitlement/verification-SLA/partition-precreate), cleanup/purge. Idempotent, no inbound surface (Infra §10).

- Search: OpenSearch index mapping + indexing consumers + query service + DB fallback (M-05).

- File storage: MinIO adapter, presigned upload issuance, media intake pipeline (scan/EXIF/variants), CDN delivery references (M-06).

Backend acceptance: import-linter boundaries green (DEC-22); no dual-write (DEC-09); coverage floors met (domain/app ≥90%, overall ≥80%); authorization matrix green; all invariants tested; OpenAPI conformance passing.

# 10. Database Deliverables

Per the Physical Database Design & ERD (authoritative):

- Schemas: 13 module schemas (identity, profiles, catalog, configuration, search, media, messaging, billing, ads, notifications, moderation, admin, analytics) with per-module PostgreSQL roles (PD-06).

- Tables: ~45 tables per §2 of the Physical DB Design, incl. Head+Version pairs (×8 config entities), the AttributeSet JSONB on catalog.listing, per-module outbox_event + processed_event.

- Migrations: Alembic, per-module branch labels, expand/contract, zero-downtime mechanics (DevSecOps §7). Deliverable: the full migration set that builds every schema from empty.

- Indexes: primary/FK/composite/partial per PD §8 (incl. partial public-visibility index, trigram fallback, geo bounding-box); no GIN on AttributeSet.

- Constraints: codegen'd CHECKs from the whitelist for closed vocabularies (PD-02), shape CHECKs, uniques (partial phone/email, invoice number, config code, version), FKs intra-schema only, immutability guard triggers (PD-07).

- Seed data: minimal bootstrap — the permission-key catalogue reference, a Super-Admin bootstrap path, default platform settings/brand defaults.

- Configuration data: an initial published configuration set (baseline categories, at least one form definition, the six product-type definitions, default roles, notification templates, search config) authored through M-04 — delivered as seed config versions so the platform is usable on first deploy.

- Partitioning: monthly range partitions on analytics.audit_entry (never dropped), analytics.metric_event (drop-purge), notifications.notification (drop-purge) from day one (PD-04).

DB acceptance: migrations build all schemas cleanly and apply expand/contract; per-module roles enforced; immutability triggers verified; seed + baseline config present; partition pre-creation job in place.

# 11. API Deliverables

The OpenAPI 3.1 Specification is authoritative (97 operations, 75 paths, 13 tags). Deliverable = a backend implementing it exactly, contract-first (generated types on the frontend). API groups:

| API group (tag) | Scope | Auth |
| --- | --- | --- |
| Authentication | OTP/email/Google flows, session issuance, recovery, logout | public → session |
| Users | account, profile, preferences, sessions, acting-context switch, closure | session |
| Business Profiles | profiles, portfolio, team, verification | session + ownership |
| Listings / Favorites | CRUD, lifecycle, images, statistics, favorites | public read / owner write |
| Categories | taxonomy + bound form (read projection) | public |
| Search | search, facets, suggest | public (rate-limited) |
| Media | presigned upload init, metadata, delete | session |
| Messaging | conversations, messages, phone-reveal, blocks, reports | session |
| Notifications | list, read status, preferences | session |
| Billing | products, orders, invoices, entitlements | session + ownership |
| Configuration (Admin) | 8-entity Head+Version lifecycle | config permission |
| Administration | moderation, verification, users, audit, reports, dashboard, payment confirm | operator permission |

Cross-cutting (all groups): URI versioning /api/v1; server-side session cookie (+ Bearer for future mobile), no JWT/refresh; Problem error envelope; cursor pagination; Idempotency-Key; LocalizedText/AttributeMap envelopes; rate-limit headers. API acceptance: OpenAPI conformance tests pass; authorization matrix per endpoint green; error envelope + pagination + idempotency behaviour verified; no undocumented endpoints.

# 12. Integration Deliverables

All external systems sit behind ports/adapters (DEC-18); no provider type crosses a module boundary. Each integration = an adapter + config + tests + a documented failure/degradation mode.

| Integration | Purpose | Adapter (port) | Config/secrets | Degradation |
| --- | --- | --- | --- | --- |
| Google OAuth | Federated sign-in (link/create by verified email) | FederatedAuthPort | client id/secret, redirect allow-list | sign-in unavailable → other methods work |
| Email provider | Transactional email (confirmations, notifications) | EmailPort | SMTP/API creds | queue+retry; non-blocking |
| SMS provider (Eskiz) | OTP + transactional SMS | SmsPort | Eskiz creds; spend cap | OTP is critical path — alert on failure |
| Yandex Maps | Geocoding + map render + radius | GeocodingPort | API key | search geo degrades; map optional |
| OpenSearch | Search read model | (search infra) | cluster endpoint/creds | DB fallback (QR-05) |
| Redis | Cache, sessions, rate-limit, pub/sub, snapshots | (infra) | endpoint/creds | cache miss → source; last-good snapshot |
| MinIO | Image object storage | StoragePort | endpoint/keys | upload unavailable → retry; existing served via CDN |

Integration acceptance: each adapter isolated behind its port with timeout + circuit breaker (SAD §15); credentials only in adapters, injected at runtime; contract/mock tests (MSW/back-end fakes); documented degradation verified. Payment providers are not integrated in Phase 1 (offline billing; PaymentProviderPort reserved for v2).

# 13. Infrastructure Deliverables

Per the Infrastructure & Deployment Architecture (authoritative) and DevSecOps strategy:

- Docker: multi-stage Dockerfiles (backend, frontend), pinned digests, non-root, slim images (DevSecOps §9).

- Docker Compose: base + per-environment overrides; the nine-service stack (nginx, web, api, realtime, worker, postgres, redis, opensearch, minio) with health checks, restart policies, resource limits, three segmented networks (Infra §3–§6).

- Nginx: TLS termination, routing (REST→api, WSS→realtime, SSR→web), edge rate-limiting/anti-scraping, security headers (Infra §16).

- Environment configuration: .env templates per environment (local/dev/staging/prod); secrets from store/Docker secrets, never committed; four-environment strategy (Infra §17, DevSecOps §2).

- Production deployment: single VM (Phase 1), readiness-gated rolling restart of api replicas, migration-before-rollout, smoke+health verification, auto-rollback to prior digest (DevSecOps §5).

- SSL/TLS: HTTPS/WSS everywhere, HSTS, automated cert management (ACME) (Infra §16).

- Backup configuration: PostgreSQL base + WAL (PITR, RPO ≤ 15m), MinIO replication, config in DB backup; OpenSearch/Redis excluded (rebuildable/cache); off-site storage; tested restore (Infra §13, INF-05).

Infra acceptance: docker compose up builds the full stack; only 443 (+80 redirect, restricted SSH) exposed; datastores private; TLS valid; backups running + a successful test restore; CI/CD deploys to staging automatically and prod on authorised release.

# 14. Testing Deliverables

Per the Engineering Playbooks and DevSecOps §13; coverage/gates are release-blocking.

| Test type | Scope | Minimum expectation | Runs |
| --- | --- | --- | --- |
| Unit | domain/app logic, invariants, mappers, hooks, form-engine | every invariant I-nn has a test; domain/app coverage ≥ 90% | every PR |
| Integration | module + real PostgreSQL/Redis; repo round-trips; outbox atomicity; migrations | per-module schema isolation; transaction+outbox verified | every PR |
| API | HTTP vs OpenAPI; authorization matrix (allow/deny per key+ownership) | contract conformance; authz matrix green (release gate) | every PR |
| Frontend (unit/component/integration) | components, hooks, mappers; a11y (axe); flows w/ MSW | axe-clean; contract-accurate mocks | every PR |
| End-to-End | register→create→publish→search→message→purchase→confirm; locale; degradation | critical journeys green | merge/nightly, staging |
| Manual acceptance | per-module acceptance packs (§16) executed with the Client/PO | every module's AC signed off | per milestone |

Overall floors: backend overall ≥ 80% (domain/app ≥ 90%); all ten quality gates (QG-01…QG-10) green; security scans (SAST/SCA/secret/image) clean of high-severity; performance smoke against SLOs. Testing acceptance: the full suite passes in CI; acceptance packs signed per milestone.

# 15. Documentation Deliverables

| Document | Audience | Content |
| --- | --- | --- |
| API Documentation | integrators, frontend, QA | rendered from the OpenAPI 3.1 spec (single source); auth, resources, errors, examples |
| Deployment Guide | DevOps | provisioning, Compose stack, env/secrets, TLS, backups, deploy/rollback, DR runbook |
| Administrator Guide | operators | user mgmt, moderation, verification, billing confirmation, audit, reports |
| Product Owner Guide | Product Owner | configuration portal — categories, forms, plans, roles, templates, settings; publish/rollback; maker–checker |
| Developer Guide | engineers, AI agents | the Engineering Playbooks (backend/frontend), module structure, AIR/FAIR rules, local setup, migrations, testing |
| Architecture set | all | the approved suite (this TT indexes it) |

Documentation acceptance: each guide delivered, reviewed, and consistent with the shipped system; API docs regenerate from the contract; Product Owner Guide enables non-technical configuration.

# 16. Acceptance Criteria (per module)

Each module (M-01…M-13) is accepted only when all six dimensions pass. Generic template (module-specific functional AC in §3):

- AC-FUNC — Functional completion: all mapped FRs implemented; the module's invariants (I-nn) proven by tests; business acceptance pack executed and signed.

- AC-UI — UI completion: all mapped screens match the UI/UX spec; four state classes present; responsive across 5 breakpoints; WCAG AA (axe-clean + manual spot-check).

- AC-API — API completion: all mapped OpenAPI operations implemented and conformance-tested; authorization matrix green; error/pagination/idempotency correct.

- AC-TEST — Testing completion: unit/integration/API/frontend tests present and green; coverage floors met; E2E for the module's critical journeys green.

- AC-DOC — Documentation completion: module README + relevant guide sections updated; config entities documented in the PO guide; ADRs for any decisions.

- AC-DEPLOY — Deployment completion: the module runs in staging within the full stack; migrations applied; health/readiness green; feature reachable end-to-end.

Platform-level acceptance: all modules accepted; all NFR verifications (§5) pass; production deployment verified; full documentation set delivered; DR restore tested.

# 17. Milestones

Logical milestones following the approved dependency build order (Playbook §15). No time or cost estimates (per instruction) — milestones are sequencing/acceptance units, not schedule.

| Milestone | Modules included | Key deliverables | Dependencies | Acceptance conditions |
| --- | --- | --- | --- | --- |
| MS-0 Foundations | shared_kernel, configuration (M-04), identity (M-01) | repo, CI/CD, Compose stack, DB schemas+migrations, config Head+Version, auth, seed config | — | stack runs; auth works; config publish/rollback works; gates green |
| MS-1 Core catalog | media (M-06), catalog (M-03) | image pipeline, listing lifecycle, dynamic form engine, wizard | MS-0 (config forms, identity) | create→publish listing with dynamic form + images; lifecycle + quota; AC met |
| MS-2 Discovery & contact | search (M-05), messaging (M-07) | OpenSearch indexing + query + fallback, facets/geo/cross-script, chat + phone-reveal/block/report | MS-1 (listings/events) | search returns/facets/geo; cross-script; chat + degradation; AC met |
| MS-3 Monetisation & trust | billing (M-08), profiles/verification (M-02), notifications (M-09) | products/orders/invoices/entitlements (offline), profiles/portfolio/verification, multi-channel notifications | MS-1 (listings), MS-0 (config products/templates) | offline purchase→invoice→confirm→entitlement; verification w/ eligibility; notifications; AC met |
| MS-4 Operations & governance | moderation+admin (M-10), analytics/audit (M-12), ads (M-13), PO portal (M-11) | admin/moderation portals, audit/reports/dashboard, banners, configuration portal UI | MS-1..MS-3 (targets to moderate/report) | moderation verbs + audit; admin queues; PO portal for all 8 entities; AC met |
| MS-5 Production readiness | all | full E2E, perf/security/a11y verification, DR drill, docs, production deploy | MS-0..MS-4 | all NFRs verified; prod deployed; DR restore tested; docs delivered; Definition of Done (project) met |

Milestone rule: a milestone closes only when every included module meets all six AC dimensions (§16) and its dependencies are accepted. MS-4 items may proceed in parallel once their targets exist (Playbook layers 3–5 parallelise).

# 18. Assumptions

Inherited from the approved documents:

- The thirteen (now nineteen) approved documents are complete, correct, and immutable; this TT does not revisit their decisions (Baseline governance).

- The Client provides, on time: business requirements sign-off, content, branding, hosting (the external-cloud VM), domain, access credentials, and milestone approvals (Contract §9; §CLIENT responsibilities).

- Hosting is external cloud outside Uzbekistan; data-residency/legal compliance is an accepted business risk owned by the Client, not engineering (DEC-07, DEC-17).

- Billing is offline (manual invoicing); no payment gateway in Phase 1 (DEC-02).

- Media is images only (DEC-10); Reviews are Phase 2 (DEC-03).

- Configuration is the platform's normal mode of business change (no deploy) (DEC-21, NFR-MAINT-001).

- The fixed technology stack (Python 3.13/FastAPI, Next.js/TS, PostgreSQL 17, Redis, OpenSearch, MinIO, Nginx, Docker) is used unchanged (SAD, DEC-16).

- Development is AI-assisted under the Engineering Playbooks; contracts (OpenAPI, event schema, interfaces) are frozen before parallel work.

- A one-month v1 target frames scope discipline (DEC-23), enforced via the descope seams (ads).

# 19. Constraints

- Technical: modular monolith (not microservices) in Phase 1; single production VM + Docker Compose (not Kubernetes); server-side sessions (no JWT/refresh); no cross-module DB access (DEC-22); expand/contract migrations only; images-only media; closed [P] vocabularies change only by release+ADR.

- Business: offline billing only; Uzbekistan-only (single country/currency); Client owns legal/regulatory/moderation-policy responsibility (Contract §3).

- Budget-related: startup budget → self-hosted open-source datastores, single VM, no managed-service sprawl, backup scope trimmed to what must be durable (Infra INF-05); vertical-first scaling.

- Phase 1 limitations: single-node fault domain (99.9% met practically with fast restore, redundancy is Phase 2); lightweight logging (centralised observability deferred, DEC-15); ads module is a descope candidate (DEC-23).

# 20. Exclusions (NOT in Phase 1)

- Native mobile applications (the contract/API are mobile-ready; apps are future).

- Online payment gateway / automated payments (billing is offline manual).

- AI-powered recommendations / personalization.

- Reviews & reputation (Phase 2, DEC-03).

- Kubernetes deployment / multi-node HA (Phase 2).

- Multi-country / multi-currency / multi-language beyond uz-Latn, uz-Cyrl, ru, en.

- Video and PDF media (images only, DEC-10).

- Centralised observability stack (metrics/tracing/log aggregation) — health/logs ship; full stack deferred (DEC-15).

- Saved-search alerts / email digests beyond what the approved endpoints support.

- Public/partner API program beyond the first-party contract.

- Any statutory data-localization/legal compliance work (Client-owned, DEC-07/17).

# 21. Requirements Traceability

The traceability matrix binds each requirement across the full chain: Business Requirement (BRD) → SRS Requirement → Functional Module → Frontend Deliverable → Backend Deliverable → API → Database → Acceptance Criteria. The matrix is maintained as the authoritative completeness artefact; the per-family rows below are the template, and every concrete FR id is enumerated in the delivered matrix (a living artefact in the repo, verified in §23).

| BRD objective | SRS req (family) | Module | Frontend | Backend | API | DB | AC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Trusted account onboarding | FR-AUTH-001…006 | M-01 | Login/Register/OTP | identity domain/app/infra | Authentication | identity | AC-M01 (session/OTP/Google) |
| User self-management | FR-USER-001…005 | M-01 | Profile/Settings | identity | Users | identity | AC-M01 (profile/prefs/closure) |
| Verified business presence | FR-PROF-001…007 | M-02 | Business/Verification | profiles | Business Profiles | profiles | AC-M02 (multi-profile/verify/badge) |
| Rich listings | FR-ADV-001…010 | M-03 | Wizard/My Ads/Detail | catalog | Listings | catalog | AC-M03 (lifecycle/images/quota) |
| Configurable catalogue | FR-CAT/FR-FORM/FR-CFG | M-04/M-11 | Config portal/Category nav | configuration | Categories/Configuration | configuration | AC-M04/M11 (Head+Version/whitelist) |
| Powerful discovery | FR-SRCH-001…005 | M-05 | Search/Facets/Map | search | Search | search+catalog | AC-M05 (facets/geo/cross-script/fallback) |
| Safe media | FR-MEDIA-001…004 | M-06 | Uploader/Gallery | media | Media | media | AC-M06 (images/scan/EXIF/non-block) |
| Buyer-seller contact | FR-MSG-001…004 | M-07 | Chat | messaging | Messaging | messaging | AC-M07 (2-party/phone/block/rate) |
| Monetisation | FR-BILL/FR-SUBS | M-08 | Subscription/Plans | billing | Billing | billing | AC-M08 (offline/entitlement) |
| Engagement | FR-NOTIF-001…004 | M-09 | Notifications | notifications | Notifications | notifications | AC-M09 (multi-channel/prefs) |
| Trust & safety | FR-MOD-001…005 | M-10 | Moderation | moderation | Administration | moderation | AC-M10 (verbs/audit) |
| Operations | FR-ADMIN-*/FR-AUDIT-002 | M-10/M-12 | Admin | admin/analytics | Administration | admin/analytics | AC-M10/M12 (users/audit/reports) |
| Insight | FR-ANALYTICS-002 | M-12 | Statistics | analytics | Listings/Administration | analytics | AC-M12 (stats/metrics) |
| Promotion inventory | FR-BANNER-001…003 | M-13 | Admin campaigns | ads | Administration | ads | AC-M13 (booking-gated/descope-safe) |

Traceability rule (mandatory): no requirement remains unmapped; every FR resolves to a module, a frontend + backend deliverable, an API operation, a DB schema, and an acceptance criterion. NFRs trace via §5. The delivered matrix (repo artefact) is checked at each milestone and at project close.

# 22. Definition of Done

"Done" is defined at four levels; each subsumes the ones below.

Feature DoD: code complete against the frozen contract; all applicable invariants covered by passing tests; unit/integration/API/frontend tests green; coverage floors met; the four UI state classes + a11y present (if UI); OpenAPI conformance (if API); requirement id referenced in tests; documentation/README updated; all quality gates (QG-01…QG-10) green; reviewed and merged via PR (no self-merge).

Module DoD: all its features Done; all six acceptance dimensions (§16) pass — AC-FUNC/UI/API/TEST/DOC/DEPLOY; the module runs in staging within the full stack; its acceptance pack signed by the Client/PO.

Milestone DoD: all included modules Done; dependencies accepted; E2E for the milestone's journeys green; NFR checks relevant to the milestone pass; milestone acceptance conditions (§17) signed.

Project DoD: all milestones Done; the full FR set implemented and traced (§21); all NFRs verified (§5); production deployment verified (smoke+health green); backups + a successful DR restore drill; the complete documentation set (§15) delivered; final client acceptance approved. Explicitly: code completed, tests passed, documentation updated, deployment verified, acceptance approved — all true simultaneously.

# 23. Validation — Consistency Review

| Check | Result | Evidence |
| --- | --- | --- |
| Alignment with BRD | Pass | §1 objectives and §21 traceability bind every BRD objective to SRS requirements, modules, and acceptance; no business goal unmapped; scope/exclusions match BRD/Vision. |
| Alignment with SRS | Pass | §4 maps every FR family and §21 enumerates concrete FR ids to module/FE/BE/API/DB/AC; §5 maps every NFR to tasks + verification; completeness is a milestone gate. |
| Alignment with Domain Model | Pass | §3 modules = the 13 bounded contexts; acceptance ties to invariants I-01…I-24; events (ListingPublished, EntitlementActivated, ConfigurationChanged, …) named per DDD; one-aggregate-per-transaction preserved. |
| Alignment with Software Architecture | Pass | §9 layers, §17 build order, and cross-module rules restate SAD/Backend Handbook (modular monolith, ports/adapters, outbox, DEC-22 isolation); import-linter is an acceptance gate. |
| Alignment with OpenAPI | Pass | §11 references the spec as authoritative (97 ops/13 tags); API acceptance = conformance + authz matrix; contract-first with generated FE types; no undocumented endpoints. |
| Alignment with Database Design | Pass | §10 restates the Physical DB Design (13 schemas, ~45 tables, Head+Version, AttributeSet JSONB, per-module roles, partitioning, immutability); migration discipline = expand/contract. |
| Alignment with Security Architecture | Pass | §5/§6/§16 enforce default-deny authz, per-module DB roles, images-only, secrets, audit, rate limits; authz matrix is release-blocking; no control weakened. |
| Alignment with Frontend Handbook/UI-UX/Design-System | Pass | §8 defers to the UI/UX spec for screens and the Design System for components; configuration-driven rendering, FAIR/DS-AI/UX-AI rules, WCAG AA, i18n carried unchanged. |
| Alignment with Backend Handbook | Pass | §9 layers/testing/coverage/boundaries and the DoD (§22) restate the Backend Handbook and DevSecOps gates; no new engineering rules introduced. |

Inconsistencies found and resolved during review:

- "Manufacturer / Seller" as roles (brief §6) — they are two of the eight profile types (closed [P] set), not roles. Resolved in §6: rendered/labelled from configuration with business-account capabilities; no hardcoded role logic — preserving the configuration-driven model.

- Deliverables implying online payments — billing is offline (DEC-02); §8/§11/§12/§20 state no payment gateway and reserve PaymentProviderPort for v2.

- Media breadth — brief-era references to video/PDF are excluded; §6/§20 fix images-only (DEC-10).

- Reviews present in some role/flow discussions — Reviews are Phase 2 (DEC-03); §1/§20 exclude them from Phase 1 scope; the traceability matrix carries no v1 Reviews requirement.

- Time/cost estimation — deliberately omitted from §17 milestones per the brief; milestones are sequencing/acceptance units only.

- Ads module scope — retained as M-13 but explicitly a descope candidate (DEC-23) with a CI-verifiable isolation property, so its removal cannot destabilise other modules — matching the approved timeline-risk mitigation.

This Enterprise Technical Task is derived from and consistent with the complete approved suite (Baseline v1.1 through the Backend Architecture & Engineering Handbook v1.0). On approval it is the primary execution and acceptance document for the Active Home project — used for development planning, client acceptance, progress tracking, AI-assisted implementation, QA, and final delivery. It translates the approved requirements into an implementation plan only; it introduces no new requirement and modifies no approved architecture, API, data model, or security control. The sole sanctioned path to change any approved decision is an ADR that amends the Baseline through governance.